## Introduction and Checklist
Study Development - PhD Project Planner |  |  | Planner version: 1.0 [2026]
Project Title:
Researcher:
Project Start Date:
Notes for completion:
Welcome to the Study Development Project PhD Planner workbook. The toolkit and this workbook have been developed by the Study Development Team, based on work by the Strategic Projects and Change team at York St John University. This workbook will provide you with guidance and practical examples (shown in red) to enable you to manage your PhD dissertation confidently to a successful conclusion. There will be guidance on how to complete each section throughout. Your thesis is a long project, and the skills you gain from thinking of it as a long project are highly valuable and transferable. Using a project planner like this can help you practice projetc thinking and have evidence of your project thinking.
When… | What … | Status
Before you start the delivery of the project work. | Complete the Project Overview tab | Not done yet
| Start thinking about how you want your supervision relationship to work. | Not done yet
| Start thinking about initial tasks | Not done yet
| Speak to your supervisor and ensure they are happy with your approach, scope and plan. | Not done yet
| Identify anything that might prevent you from achieving the project's objectives (i.e. your risks) | Not done yet
| Keep updating your plan (what is in progress, completed, waiting for something else etc.) | Not done yet
During the process of completing your thesis. | Keep updating your supervisor on progress | Not done yet
| Keep checking your risks and issues register. | Not done yet
| Let your supervisor know if you have any blockers they can help resolve. | Not done yet
| Regularly update the Project Progress Report. | Not done yet
| Keep logging the decisions you are making as you go along | Not done yet
| Check all the tasks in the plan have been marked as completed | Not done yet
Continue to update your research log.
As you complete/near completion. | Keep filling in the Viva Preparation sheet with potential questions and avenues of inquiry. | Not done yet
| Go through the editing and proofreading checklist. | Not done yet
| Update corrections sheet post-viva. | Not done yet

## Project Overview
Project Overview
Notes for completion:
In this section, you are going to describe what you hope your thesis will deliver and what constraints (time, funding, deadline, other life commitments, etc.) might hinder your progress. This section will likely change as your thesis progresses, so try to revisit this page every few months. Use this page to orient your work, both intellectually and practically.
Purpose of my thesis: | What is the purpose of my thesis? What is my research question? What problem, gap, or tension in my field am I trying to address? Why does this project matter? Who is my ideal reader?
Personal Motivations | Why do I care about this project? What first drew me to this topic? What will finishing my project feel like? What does my thesis mean to me?
Contribution and Originality | What is genuinely original about my project? What does my project do differently from other people who have worked on the same subject? How does my research extend or reshape the field? What might an external examiner say is my main contribution to the field?
Key Milestones: | Do you have a deadline by which you need to submit your thesis? What are some key milestones (chapter drafts, etc.) that you will need to meet?
| Milestone | Date
| Example: Draft first chapter with full referencing | 2026-03-01
| Example: Draft second chapter | 2026-10-01
| Example: Draft third chapter | 2027-03-01
| Example: Draft fourth chapter | 2027-11-01
| Example: Draft introduction and conclusion | 2028-03-01
Scope: | What is the scope of my project? Where is the boundary between what you will and won't discuss? What would make the project unfinishable? If you had to lose a chapter/section, what would go first? What am I not doing? What materials am I excluding and why?
Note on A8: A project milestone is a task of zero duration that shows an important achievement in a project. The milestones should represent a clear sequence of events that incrementally build up until your project is complete
Note on A22: List what key deliverables are in scope. Examples in a well-defined scope will ensure the boundaries of the project are understood.

## Supervision
Supervision Log
Notes for completion:
In this section, you should first complete the "Purpose" and "Roles and Responsibilities" section of the planner (ideally following discussion with your supervisor). This will allow you and your supervisor to discuss and manage expectations around the supervisory relationship from the start. You should then use the "Supervision Log" section to track your supervisory meeting, any key feedback or new decisions, and any actions agreed upon.
Purpose of Supervision | How do you want supervision to work? What do you want from your supervisor, both intellectually and practically? What kind of feedback is the most useful to you?
Roles and Responsibilities | How often would you like to meet? How will you prepare for meetings? How will you communicate problems early? What do you expect your supervisor to help with? What kind of guidance do you need the most? Think about the kind of feedback you would like (written/verbal) and the balance between direction and autonomy that you would like to find.
Supervision Log | Preparation (work sent in advance/questions prepared): | Key Feedback: | Main Decisions Made: | New Directions or Changes? | Actions Agreed
Supervision Meeting 1 Date:
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8

## The Plan
The Plan
Notes for completion:
Think of this as your to-do list: what are all the individual things that need to happen for you to make your research a success? Top tips: - Think about the order in which these need to happen. Is there anything in your list that needs something else to happen first? - How do all these things fit with the milestones you listed in the Project Overview tab? - Try to break larger tasks down into smaller chunks.
Task ID | Description | Task status | Start Date | Due Date | Actual Completion Date | Notes
1 | Example: Identify key sources and being preliminary draft of literature review. | In progress | 2026-04-10 | 2026-05-23
2 | Example: Produce draft of first chapter | Not started | 2026-06-10 | 2026-12-23
3 | Example: Prepare a draft of a proposed journal article. | Not started |  | 2026-01-23
Note on D5: When do you want this task completed?
Note on E5: When do you want this task completed?

## Risks and Issues
Risks and Issues
Notes for completion:
This is a list of things that go wrong (issues) while you are trying to deliver your thesis and a list of things that could go wrong (risks). Top tips: - Think about different types of risk: personal (health, mental wellbeing, financial, competing commitments), academic (any ethical considerations, etc), time management, supervisory/institutional risk, etc. - Ask yourself, what is the likelihood of this risk and what will its impact be on my project? - For issues: what is a blocker for progress on your project? Note it down - it is an issue. - What is behind schedule on your plan and why? Note it down. - When a risk comes true, it moves from being a risk to an issue. Record that change here.
Type | Description | Status | Date issue/risk raised | Probability | A | Impact | B | C | Priority | Impact to the project | Mitigation/Action needed | Date closed | Notes
Issue | Example: No access to key texts from library | Open |  | High |  | Medium |  |  | High | Unable to complete literature review and introduction. Research notes incomplete. | Speak to library about purchase/inter-library loan.
Risk | Example: Supervisor on illness leave | Open |  | Medium |  | High |  |  | High | Lack of supervision and feedback | Discuss plan with supervisor, look at alternative supervisory options in the short term.
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[7 empty] | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
[5 empty] | 0 |  | 0 | 0
Note on J5: Rank these high, medium or low to denote how often you think you need to keep an eye on these. Those with the biggest impact that are most likely to occur should be prioritised high.

## Decisions
Decisions
Notes for completion:
This is a list of all the decisions made about your research. It is important to keep this list up to date so that you can refer back to it as your thesis progresses. It is also useful to keep in mind when you prepare for your viva; it is likely that you will be asked about key decisions that you made during the course of your research. You can use these as preparatory notes as you prepare for your viva.
Decision description | Decision outcome | Date decision made | Who asked for the decision? | Who made the decision?

## Research Methods
Methods and Methodology
Notes for completion:
This section is where you explain how you are going to answer your research question(s), and why these methods are appropriate. This section may evolve as your project develops. Focus on justifying your choices and showing that they are deliberate and appropriate for your research.
Methodological Approach
What is your overall methodological approach (e.g. qualitative, quantitative, mixed methods, practice-based, theoretical)? Why is this approach appropriate for your research question(s)? What kinds of knowledge does it allow you to produce, and what does it not allow you to do?
Theoretical Frameworks
What theories, models, or intellectual traditions underpin your methodology? How do these shape the way you approach your research and interpret your findings?
Research Design
How is your study structured? What are the main stages or phases of your research, and how do they relate to one another? Is your design fixed or iterative?
Data/Materials
What data, materials, or sources are you working with? Where do they come from, and what constraints exist around access, availability, or quality?
Ethical Considerations
What ethical issues arise in your research? Do you require ethical approval, and how are risks being managed?

## Research Log
Research Log
Notes for completion:
This is a list of your research sources, designed to help you to organise, summarise, and evaluate each source in one place. Each row should contain one source with key details such as author, publication information, main ideas, and any notes you have made. Keep it updated as you research, and use this page to complete your final reference list / bibliography. Consider using this alongside a Reference Manager which can help automate the creation of a reference list: https://www.yorksj.ac.uk/library/referencing/reference-management-tools/
ID Number | Author(s) | Year | Title | Reference (APA/Harvard…) | Type of Resource | Topic/Keywords | Abstract | Research Question | Main Findings | Notes
Example: 1 | Hirsch, Edward. | 1991 | The Imaginary Irish Peasant | Hirsch, Edward. “The Imaginary Irish Peasant.” PMLA, vol. 106, no. 5, 1991, pp. 1116–33. JSTOR, https://doi.org/10.2307/462684. Accessed 9 Apr. 2026. | Journal Article | peasantry, irish literature, modernism, colonialism, rurality | In the late nineteenth and early twentieth centuries the Irish peasant was a figure encoded with literary, social, and political meaning, and to speak or write about that central image of Irish identity in the context of the time was to participate in a special kind of cultural discourse, far removed from the changing realities of rural life. The portraits of the peasant generated by different Irish poets, dramatists, fiction writers, and antiquarians were often radically opposed to one another; in fact, each writer undertook to rewrite or to reconceptualize the peasant characters imagined by predecessors and contemporaries. Thus W. B. Yeats and Douglas Hyde created portraits that not only rivaled each other but aimed primarily at overturning the prevailing English colonial stereotype reflected in the stage Irishman. These portraits were in turn rewritten by John Synge, even as Yeats's, Hyde's, and Synge's were reworked in divergent ways by James Joyce, Flann O'Brien, and Patrick Kavanagh. | Were Irish literary depictions of the peasant accurate to the sociological reality? | No - the peasant was a literary creation that served numerous ideological/cultural ends, depending on the author. | "This interest deeply intensified during the early years of the Irish Literary Revival-indeed, it was in this period that the Irish peasant was fundamentally "created" and characterized for posterity. By placing the peasant figure at the heart of their enterprises, key Revival writers such as W. B. Yeats, John Synge, George Russell (AE), Isabella Augusta Gregory, and Douglas Hyde were partici- pating in a complex cultural discourse motivated by crucial eco- nomic, social, and political needs, as well as by pressing cultural concern." (1116)

## Editing and Proofreading
Editing and Proofreading - Checklist
Notes for completion:
This page allows you to keep track of the editing and proofreading stage of submitting your thesis. Ideally, you should begin this process around six months before you plan to submit. Tick off each task as you complete it.
Three to six months before submission: | Y/N?
Review and finalise title
Review and finalise abstract
Review and finalise terms, concepts, and definitions
Confirm the expected format of your thesis (page layout, citation style, acceptable digital formats, etc.
Two to four months before submission | Y/N?
Review and finalise chapter titles and sub-headings.
Complete any missing or incomplete sections.
Respond to any outstanding supervisor feedback.
Redraft and complete introduction, and introductions, transitions, and conclusions in each chapter.
Identify and review the most problematic parts of your thesis.
Highlight your argument and remove excess material.
Redraft conclusion.
One to two months before submission: | Y/N?
Check for consistent use of spelling terms throughout.
Check all spelling, punctuation, and grammar for accuracy and consistency.
Check all references and citations for accuracy.
Finalise bibliography.
Check formatting.

## Viva Preparation
Viva Preparation
Notes for completion:
Keep this list updated as you write with potential viva questions and answers. We have included some typical viva questions, but you will also need to anticipate questions that are specific to your project and add them below. We suggest doing this with your supervisor.
Viva Question | Answer Notes
Why did you decide on your particular research question?
How did your thinking about this topic develop over the course of your research?
Who are the key influences on your research and why?
Were there any surprises that you encountered during the course of your research?
What is original about your thesis?
How do your conclusions develop the literature in your field?
What do you think is the weakest part of your thesis?
What do you think is the strongest part of your thesis?
In what directions could this research be taken further in the future?

## Project Progress Report
Research Progress Report | [6 empty] | Notes for completion:
Project: | 0 | [5 empty] | In this section you are going to update the progress of your project. To do this: - update the report date - right-mouse click on the tables below (tasks and risks) and click refresh. - transpose the figures to the tables on the left for tasks and risks - update the RAG status for your milestone (RED = will not be completed on time, AMBER = may be completed on time, GREEN = will be completed on time) - update what you have spent in your budget. - if you are print this tab - just print the first page so that these notes do not appear.
Project Manager: | 0
Report Date:
Project Tasks | Number | Open Risks and Issues | Number | Milestones | Date | RAG Status
Not started | 3 | High | 1 | Example: Draft first chapter with full referencing | 2026-03-01 | 
In progress | 0 | Medium | 1 | Example: Draft second chapter | 2026-10-01 | 
Completed | 0 | Low | 0 | Example: Draft third chapter | 2027-03-01 | 
Waiting for another task | 0 | Total Open Risks/Issues | 2 | Example: Draft fourth chapter | 2027-11-01 | 
Total Tasks | 3 |  |  | Example: Draft introduction and conclusion | 2028-03-01 |  |  |  | Risks
|  |  |  | 0 | 0 |  | Row Labels | Count of Task ID | Status | Open
[7 empty] | Not started | 3 | Type | (All)
[7 empty] | (blank) | 17
[7 empty] | Grand Total | 20 | Row Labels | Count of Type
[9 empty] | High | 1
[9 empty] | Medium | 1
[9 empty] | Grand Total | 2

## Corrections
Corrections
Notes for completion:
Congratulations! You've submitted your thesis, and you've passed with either major or minor corrections. Use this page to keep track of your corrections and your progress,
Task ID | Description | Task status | Due Date | Actual Completion Date | Notes
1 | Revise conclusion to present argument more clearly | In progress
2 | Fix typos in the introduction and chapter one. | Not started
Note on D5: When do you want this task completed?